## Tests
TC_NO | Module | Device | Test | Execution Steps | Expected Result | Actual Result | Test Status | Comments
TC01 | Dashboard | Desktop Chrome | Verify Priceify Dashboard homepage static and dynamic content. Make sure the static content match with given Priceify Naming principles Doc starting from page 16. See Comments column. For dynamic content, please compare with data in other modules. |  |  | Static content are matching the naming principles. Dynamic content need testing later | Partially passed | https://docs.google.com/document/d/1neq3ubJey2WdscBN9sxmY7ln8nRjOMr7QRajzU_RXag/edit?tab=t.0
TC02 | Dashboard | Desktop Chrome | Verify test list filters functionality (All, Running, etc.) |  |  | As expected | Passed
TC03 | Dashboard | Desktop Chrome | Verify Search tests works correctly |  |  | Search is working fine and it currently show results matching test title only. But it could be improved by adding support to showing results based on other test properties such as (Hypothesis, Products etc.) | Passed
TC04 | Dashboard | Desktop Chrome | Verify All Test list actions for Draft tests |  |  | Draft test test has more action options than other draft tests. Issue No.11 | Failed
TC05 | Dashboard | Desktop Chrome | Verify All Test list actions for Running tests |  |  | Can't pause a running test. Issue 8 | Failed
TC06 | Dashboard | Desktop Chrome | Verify All test list actions for Paused tests |  |  | Can't pause a running test. Issue 8 | Failed
TC07 | Dashboard | Desktop Chrome | Verify all links are working (+ New Test, App Settings, Store setup) |  |  | As expected | Passed
TC08 | Dashboard | Desktop Chrome | Test Create is locked feature. Leave the plan or store setup incomplete and verify the locked banner content matching the Doc. (See the bottom of the page 17) |  |  |  | Not run | https://docs.google.com/document/d/1neq3ubJey2WdscBN9sxmY7ln8nRjOMr7QRajzU_RXag/edit?tab=t.0
TC09 | Create New Test | Desktop Chrome | Step -1: Verify first step contents, form validation, both price and offer test option selection. |  |  | Form validation is as expected Both price and offer selection is working Regarding Content: Helper text mentioned in the doc "Optional, for your notes only" is missing in the app. Issue 16. | Passed | Helper text issue fixed
TC10 | Create New Test | Desktop Chrome | Verify user is able to create a test completing all 5 steps - happy path |  |  | As expected | Passed
TC11 | Create New Test | Desktop Chrome | Step -2: Verify user is able to add and remove variations |  |  | As expected | Passed
TC12 | Create New Test | Desktop Chrome | Step -2: Verify form validation is working properly |  |  | As expected | Passed
TC13 | Create New Test | Desktop Chrome | Step -2: Verify data remain as is if user goes back from step 2 to step 1 |  |  | As expected | Passed
TC14 | Create New Test | Desktop Chrome | Step -2: Verify split evenly button distributes the traffic evenly accoss all variations |  |  | As expected | Passed
TC15 | Create New Test | Desktop Chrome | Step -2: Verify Traffic split info (i) modal |  |  | As expected | Passed
TC16 | Create New Test | Desktop Chrome | Step -3: Verify step 3 default page content |  |  | As expected | Passed
TC17 | Create New Test | Desktop Chrome | Step -3: Verify all products loaded automatically in Browse products section |  |  | All products loaded. Product counts mentioned in the message need to be verified | Partially passed
TC18 | Create New Test | Desktop Chrome | Step -3: Verify Browser products opens the product picker modal. Also verify the product picker modal content and behaviour |  |  | Browse products popup has multiple issues. See issues 21,22,23,24 | Failed
TC19 | Create New Test | Desktop Chrome | Step -3: Verify clicking All products shows all products in the products table below |  |  | List shows duplicate products which are added in other running tests. See issue 24 | Failed
TC20 | Create New Test | Desktop Chrome | Step -3: Select Pick specific products and verify AI suggested option's behaviour. Test the AI suggestion form with both Suggest and Re-suggest buttons and
TC21 | Create New Test | Desktop Chrome | Step -3: Verify Bulk adjust option's form and it's behaviour. Make sure bulk suggestion applies to the products accordingly. Test the form thoroughly.
TC22 | Create New Test | Desktop Chrome | Step -3: Verify Set manually option and it's behaviour.
TC23 | Create New Test | Desktop Chrome | Step -3: Verify product table data, filter, search, Expand and Collaps buttons, Paginations and the price input fields' validation
TC24 | Create New Test | Desktop Chrome | Step -3: Switch between variations and make sure same features work on other variations.
TC25 | Create New Test | Desktop Chrome | Step -4: Verify user can select all options of Device type, Traffic source, Audience segment
TC26 | Create New Test | Desktop Chrome | Step -4: Verify Country combo box with Inlcude and Exclude options. Also make sure countries can be removed
TC27 | Create New Test | Desktop Chrome | Step -4: Verify Revenue guardrail content and it's actions (info popup, toggle and the only input field)
TC28 | Create New Test | Desktop Chrome | Step 5: Verify Review & launch step content and Finally verify clicking Launch test button successfully launches the test. Make sure after successful launch, it opens the experiment details page. |  |  | Final submission is very slow when Launch button is clicked on step 5. After clicking, the Launch button takes ~5 seconds to react then the loader/spinner appears.
TC29 | Test details | Desktop Chrome | Verify test details page content for Overview
TC30 | Test details | Desktop Chrome | Verify all links are clickable and working
TC31 | Test details | Desktop Chrome | Verify history page content and its links
TC32 | Test details | Desktop Chrome | Verify Settings page content and all edit popup forms including Edit Metric and Edit Guardrail.
TC33 | Test details | Desktop Chrome | Verify Reference & Identifiers section and it's links
TC34 | Test details | Desktop Chrome | Verify all test details page actions for each of the different types of tests (Draft, Running, Paused, Finished and Archive)
TC35 | Store Setup | Desktop Chrome | Verify store setup page content for a Ready to launch store
TC36 | Store Setup | Desktop Chrome | Verify setting up a new store and perform store setup to make it ready for launching tests
TC37 | Store Setup | Desktop Chrome | Verify store setup behaviour with Theme connection = disabled
TC38 | Store Setup | Desktop Chrome | Verify store setup with Checkout pricing functions disabled. - Only price tests enabled - Only offer tests enabled - Both disabled
TC39 | Store Setup | Desktop Chrome | Verify Refresh status button behaviour
TC40 | Store Setup | Desktop Chrome | Verify price locations mapping with both Mapped and Unmapped status
TC41 | Store Setup | Desktop Chrome | Verify Auto-detect prices feature automatically scans and redirects to App settings > Price locations
TC42 | Store Setup | Desktop Chrome | Verify Edit price locations button redirects to App settings > Price locations
TC43 | Store Setup | Desktop Chrome | Verify Back to Tests and New Test buttons open the relevant pages
TC44 | App Settings | Desktop Chrome | Verify app settings Plan & Usage tab content when plan is active and all tests unlocked
TC45 | App Settings | Desktop Chrome | Verify app settings Plan & Usage tab content when plan is Inactive and all tests are not unlocked
TC46 | App Settings | Desktop Chrome | Verify Plan & usage page links and buttons
TC47 | App Settings | Desktop Chrome | Verify Result settings content and the form
TC48 | App Settings | Desktop Chrome | Verify price locations tab content and the form
TC49 | App Settings | Desktop Chrome | Verify price locations tab's auto detect price popup content and it's behaviour
TC50 | App Settings | Desktop Chrome | Verify global JS/CSS editor using both Javascript and CSS options. Test Enabled flag as well.
TC51 | Help & docs | Desktop Chrome | Verify Answers tab content and all links
TC52 | Help & docs | Desktop Chrome | Verify Support tickets list page content and functionalities (click on a ticket, Click on the alert link above the table if a reply is waiting on you)
TC53 | Help & docs | Desktop Chrome | Verify New ticket form validation and successful creation of tickets. Verify Answers link.
TC54 | Help & docs | Desktop Chrome | Verify user can create a ticket for each category
TC55 | Cross Browser/Device tests | Desktop Firefox | Verify all features are responsive and nothing is broken on firefox
TC56 | Cross Browser/Device tests | Desktop Safari | Verify all features are responsive and nothing is broken on Safari
TC57 | Cross Browser/Device tests | iPhone latest Safari | Verify all features are responsive and nothing is broken on latest iPhone
TC58 | Cross Browser/Device tests | Table Chrome | Verify all features are responsive and nothing is broken on Android Tablet Chrome
TC59 | Cross Browser/Device tests | iPad Safari | Verify all features are responsive and nothing is broken on iPad Safari

## Test Evidence
TC01
| Running | Draft | Finished | Archived
TC02
TC03
TC04
TC05
TC07
TC09
After fixing issue 16
TC10
TC11
TC12
TC13
TC15
TC16
TC18

## Issues
ID | Summary | Expected result | Steps to reproduce | Status | Screenshot/Video | Remarks
1 | Products are not showing in step 2. Can't proceed further with test creation module |  |  | Fixed | SS01
2 | Test Tj - basket redesign is launched but the status is still showing as Draft |  |  | Open | SS02
3 | When Edit test button is clicked on a paused test, it opens the new test form instead of the edit page. | Should open edit form |  | Fixed | https://echologyxcom-my.sharepoint.com/:v:/g/personal/tanjil_echologyx_com/IQAtZanHWF65RLPVJ_StaO5aAadNnLTf1YH09ljtw-Y5TwE?e=amAkIp | Evidence of this fix: https://echologyxcom-my.sharepoint.com/:v:/g/personal/tanjil_echologyx_com/IQDiyMnqVQ9UQ766WOYc2vsVAYlqATP9mPDMBmXKQKTlbN0?e=bGOi8n
4 | If I click App - settings > Manage plan, it throws a page not found error message | Manage plan details should be displayed instead of page not found |  | Open |  | Feature not yet fully implemented
5 | When I move a finished to Archive, the status remains Finished with a light grey background. | Status should be something like Archived |  | Fixed | https://echologyxcom-my.sharepoint.com/:v:/g/personal/tanjil_echologyx_com/IQC3mK2cl5GhSJdeIajYELAyAS35jtwBzWPYZmCzwPhvUu4?e=1as8cL&nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJTdHJlYW1XZWJBcHAiLCJyZWZlcnJhbFZpZXciOiJTaGFyZURpYWxvZy1MaW5rIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXcifX0%3D | Fixed: https://echologyxcom-my.sharepoint.com/:v:/g/personal/tanjil_echologyx_com/IQC3hL8_HCNeSoJHD0pqyUzgAbMoYWQ5PJL3BlRBqt0kFng?e=tNyz5z
6 | Can't see any visitor count if I visit the variation after launching a test |  |  | Open
7 | Paused test becomes finished if moved to archive - if restored again it becomes finished | Paused test status should change to Archived when moved to archived. When restored the status should change back to paused |  | Fixed | https://echologyxcom-my.sharepoint.com/:v:/g/personal/tanjil_echologyx_com/IQD7mrPsPv7XSJFJyUZTB0UwATzdo5m-qcs9iUz2bTLEVRM?e=FS2z07 | https://echologyxcom-my.sharepoint.com/:v:/g/personal/tanjil_echologyx_com/IQC3hL8_HCNeSoJHD0pqyUzgAbMoYWQ5PJL3BlRBqt0kFng?e=tNyz5z
8 | I am unable to pause a running test |  |  | Open | https://echologyxcom-my.sharepoint.com/:v:/g/personal/tanjil_echologyx_com/IQDLGUKnIDyMTpwiqJZabWl2AcHLrrjXJ9LmxxkH5dcGn1o?e=UTuplH | SS31
9 | Search is working fine and it currently show results matching test title only. But it could be improved by adding support to showing results based on other test properties such as (Hypothesis, Products etc.) |  |  | Fixed | Fixed: SS18, SS19, SS20, SS21
10 | No success message displayed after deleting a test |  |  | Fixed | https://echologyxcom-my.sharepoint.com/:v:/g/personal/tanjil_echologyx_com/IQDGCCYdMGhtRYIhRE-MrTzOASLayuXQ75c1h-42K8Cvt5E?e=uAsJs4 | Fixed: SS22, 23
11 | I found a test who's status is Draft in the list but on the details page it shows queued. Also there are overview, history and settings tab available in this test which usually be available for a running test. Moreover, on the list page the same draft test shows additional test actions (View results, Launch test). Can you investigate please. | Draft tests should not have test details like a running test. |  | Open
12 | Step 3: The All products card copy reads “Include every eligible product available on your live store.” instead of “Include every product in your catalog.” |  |  | Fixed | SS05 | Fixed: SS24
13 | Step 4: The entire Secondary metrics selection field is omitted. |  |  | Fixed | SS06 | Fixed: SS25
14 | Step 4: The Revenue guardrail text has deviated from the proposed copy. |  |  | Open | SS07 | The content still does not match the doc. SS26
15 | Step 5: The review summary layout uses inline tags (Test, Traffic, Audience, Results, Safety) rather than the planned full-section breakdown (Basics, Products & prices, etc.). |  |  | Open | SS08
16 | Step 1: Helper text mentioned in the doc "Optional, for your notes only" is missing in the app. |  |  | Fixed | SS09
17 | Step 2 & Step 3: Labels should use the correct capitalization to match the doc. |  |  | Open | SS10, SS12
18 | Step 2: There has to be at least some gap between the add variation button and the helper text below. Now it looks congested. |  |  | Open | SS11
19 | Final submission is very slow when Launch button is clicked on step 5. After clicking, the Launch button takes ~5 seconds to react then the loader/spinner appears. |  |  | Open | https://echologyxcom-my.sharepoint.com/:v:/g/personal/tanjil_echologyx_com/IQC4E_p1auOlSbF6kZZFkjA_AetF8od3I0pQnz5ZG9tECLI?e=wxCEWY
20 | User is able to delete Variation B when there are 3 variations (A,B,C) added on Step 2. This allows the test to have variations A & C for a 2 variation test which does not make perfect sense. A test created with variation A & C allows you to add another variation C later by editing it which makes the variant list as A, C, C where C is duplicate. | Do not allow adding a duplicate variant on edit page. |  | Open | SS13, SS14, SS15, SS16 Video: https://echologyxcom-my.sharepoint.com/:v:/g/personal/tanjil_echologyx_com/IQDHXUwsRsCbQYaRRZNZ_kSpAad1ymDZFVUQ0T04uTklJUA?e=sfHQb0 | Discussed with Ripon vai to apply solution by addming B back to the test.
21 | Step 3 - Browse products popup - Collection-Categories search field overlaps with the button row above |  |  | Open | SS27
22 | Step 3 - Browse products popup displays only 200 of 296 products and a message is shown at the bottom of the table instructing to search and find the other 96 products. | List should display all 296 products with a pagination |  | Open | SS29, SS30
23 | Step 3 - Browse products popup displays only 1 collection, but in shopify there are 3. |  |  | Open | SS28
24 | Step 3 - Browse popup displays a product which is already added in another running test. The same product is also available on the product table when All products option is selected. |  |  | Open | SS32, SS33

## Issue Screenshots
SS01
SS02
SS03
SS04
SS05
SS06
SS07
SS08
SS09
SS10
SS11
SS12
SS13
SS14
SS15
SS16
SS17
SS18
SS19
SS20
SS21
SS22
SS23
SS24
SS25
SS26
SS27
SS28
SS29
SS30
SS31
SS32
SS33

## Questions - Confirmations
Where is this text coming from?